## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | US 01 | As a visitor, I should be able to “Register” to the application as a buyer by providing my credentials | should | 3 | Abhishek Tarra | 3- Completed
1 | 1 | US 02 | As a visitor, I should be able to “Register” to the application as a seller by providing my credentials | should | 3 | Abhishek Tarra | 3- Completed
1 | 1 | US 03 | As a Buyer, I should be able to “Login” to the application as a Buyer by providing my credentials | must | 3 | Abhishek Tarra | 3- Completed
1 | 1 | US 04 | As a buyer, I should be able to perform some actions on the user microservice application . | could | 13 | Abhishek Tarra | 3- Completed
1 | 1 | US 05 | As a Buyer, I should be able to perform some actions on order microservices application | could | 13 | Saurabh Ravindra Potdar | 3- Completed
1 | 1 | US 06 | A privileged buyer, must be able to buy unlimited quantity of a specific product | could | 3 | Abhishek Tarra | 3- Completed
1 | 1 | US 07 | As a Seller, I should be able to “Login” to the application as a Seller by providing my credentials | must | 3 | Abhishek Tarra | 3- Completed
1 | 1 | US 08 | As a Seller, I should be able to perform some actions on product microservice | could | 13 | Madhuri Munnelli | 3- Completed
1 | 1 | US 09 | As a Buyer, I should be able to deactivate my current account from the application | could | 3 | Abhishek Tarra | 3- Completed
1 | 1 | US 10 | As a Seller, I should be able to deactivate my current account from the application | could | 3 | Abhishek Tarra | 3- Completed
1 | 1 | US 11 | As a Visitor, must be able to browse through the available products | could | 1 | Madhuri Munnelli | 3- Completed
2 | 2 | US 12 | Sonar analysis and deployment of microservice aws | must | 13 | Nikhila Juttu | 3- Completed
2 | 2 | US 13 | Sonar analysis and deployment of microservice aws | must | 13 | Saurabh Ravindra Potdar | 3- Completed
2 | 2 | US 14 | Sonar analysis and deployment of microservice aws | must | 13 | Madhuri Munnelli | 3- Completed
100
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on F2: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 83.5 | 39 | 29 | 15.5
SPRINT 1 BACKLOG
US-01 | T1 | Validation of Name | 2021-09-01 | 2021-09-01 | Abhishek Tarra | Coding | 3- Completed | 1 | 1
| T2 | validation of password | 2021-09-01 | 2021-09-01 | Abhishek Tarra | Coding | 3- Completed | 1 | 1
| T3 | validation of email | 2021-09-01 | 2021-09-01 | Abhishek Tarra | Coding | 3- Completed | 0.5 | 0.5
| T4 | validation of phone number | 2021-09-01 | 2021-09-01 | Abhishek Tarra | Coding | 3- Completed | 0.5 | 0.5
| T5 | Implementation of Service and contoller class | 2021-09-01 | 2021-09-02 | Abhishek Tarra | Coding | 3- Completed | 2.5 | 1.5 | 1
T6
T7
T8
US-02 | T1 | Validation of Name | 2021-09-01 | 2021-09-01 | Abhishek Tarra | Coding | 3- Completed | 0.5 | 0.5
| T2 | validation of password | 2021-09-01 | 2021-09-01 | Abhishek Tarra | Coding | 3- Completed | 1 | 1
| T3 | validation of email | 2021-09-01 | 2021-09-01 | Abhishek Tarra | Coding | 3- Completed | 0.5 | 0.5
| T4 | validation of phone number | 2021-09-01 | 2021-09-01 | Abhishek Tarra | Coding | 3- Completed | 0.5 | 0.5
| T5 | Implementation of Service and contoller class | 2021-09-02 | 2021-09-02 | Abhishek Tarra | Coding | 3- Completed | 2 | 2
T6
US 03 | T1 | Validation of login details | 2021-09-02 | 2021-09-02 | Abhishek Tarra | Coding | 3- Completed | 1 | 1
| T2 | Implementation of Service and contoller class for login | 2021-09-02 | 2021-09-03 | Abhishek Tarra | Coding | 3- Completed | 2.5 | 1 | 1.5
T3
T4
T5
US 04 | T1 | Validation in quantity and delivery addres | 2021-09-03 | 2021-09-03 | Abhishek Tarra | Coding | 3- Completed | 1 | 1
| T2 | Add products from product details page to Wishlist | 2021-09-02 | 2021-09-04 | Abhishek Tarra | Coding | 3- Completed | 3 | 1 | 0.5 | 1.5
| T3 | remove product from wish list and move products from wish list to cart | 2021-09-03 | 2021-09-06 | Abhishek Tarra | Coding | 3- Completed | 3.5 | 1.5 | 1 | 1
| T4 | Able to add a product from product details page to Cart | 2021-09-03 | 2021-09-06 |  | Coding | 3- Completed | 4 | 2 | 0.5 | 1.5
| T5 | Able to manage the Cart in the Cart page | 2021-09-03 | 2021-09-06 | Abhishek Tarra | Coding | 3- Completed | 3.5 | 0.5 | 2 | 1
| T6 | must able to check out cart item | 2021-09-03 | 2021-09-04 | Abhishek Tarra | Coding | 3- Completed | 3.5 | 1 | 2.5
T7
T8
US 05 | T1 | must be able to view the past orders. | 2021-09-01 | 2021-09-04 | Mayank Kumar Athia | Coding | 3- Completed | 4.5 | 1.5 | 1 | 2
| T2 | must be able to reorder previously ordered products by Validating that the buyer has made purchases before | 2021-09-01 | 2021-09-06 | Mayank Kumar Athia | Coding | 3- Completed | 7 | 2 | 3 | 2
| T3 | must be able to accumulate reward points based on orders | 2021-09-03 | 2021-09-06 | Mayank Kumar Athia | Coding | 3- Completed | 6 | 2 | 2 | 2
| T4 | place a new order for buyer | 2021-09-03 | 2021-09-04 | Mayank Kumar Athia | Coding | 3- Completed | 2 | 1 | 1
| T5 | Get all order | 2021-09-04 | 2021-09-06 | Mayank Kumar Athia | Coding | 3- Completed | 2.5 | 1 | 1.5
| T6 | Delete orders | 2021-09-04 | 2021-09-06 | Mayank Kumar Athia | Coding | 3- Completed | 1.5 | 1 | 0.5
US06 | T1 | Able to add a product from product details page to Cart | 2021-09-02 | 2021-09-04 | Nikhila Juttu | Coding | 3- Completed | 3 | 0.5 | 2 | 0.5
| T2 | Able to manage the Cart in the Cart page | 2021-09-03 | 2021-09-06 | Nikhila Juttu | Coding | 3- Completed | 2.5 | 1 | 1 | 0.5
| T3 | Must be able to subscribe to monthly delivery of selected products | 2021-09-04 | 2021-09-06 | Nikhila Juttu | Coding | 3- Completed | 3 | 0.5 | 0.5 | 2
T4
T5
US 07 | T1 | Validation of email and password | 2021-09-02 | 2021-09-02 | Nikhila Juttu | Coding | 3- Completed | 0.5 | 0.5
| T2 | implementation of service and controller class | 2021-09-02 | 2021-09-03 | Nikhila Juttu | Coding | 3- Completed | 2.5 | 1 | 1.5
T3
T4
T5
T6
US 08 | T1 | validation of name | 2021-09-02 | 2021-09-02 | Sreekuttan O M | Coding | 3- Completed | 0.5 | 0.5
| T2 | validation of Description | 2021-09-02 | 2021-09-02 | Sreekuttan O M | Coding | 3- Completed | 0.5 | 0.5
| T3 | validation of price | 2021-09-02 | 2021-09-02 | Sreekuttan O M | Coding | 3- Completed | 0.5 | 0.5
| T4 | validation of stock | 2021-09-02 | 2021-09-02 | Sreekuttan O M | Coding | 3- Completed | 0.5 | 0.5
| T5 | validation of image | 2021-09-02 | 2021-09-02 | Sreekuttan O M | Coding | 3- Completed | 0.5 | 0.5
| T6 | able to update stocks of products | 2021-09-02 | 2021-09-03 | Sreekuttan O M | Coding | 3- Completed | 1.5 | 0.5 | 1
| T7 | able to add and remove products | 2021-09-03 | 2021-09-06 | Sreekuttan O M | Coding | 3- Completed | 2.5 | 1 |  | 1.5
T8
US 09 | T1 | Buyer should be able remove their account from the application by making their account inactive. | 2021-09-03 | 2021-09-06 | Nikhila Juttu | Coding | 3- Completed | 2.5 | 1 | 1.5
US 10 | T1 | Seller should be able to remove their account from application and disable all the products from the seller. | 2021-09-03 | 2021-09-06 | Nikhila Juttu | Coding | 3- Completed | 3 | 2 | 1
US 11 | T1 | Search Products based on category of the product | 2021-09-02 | 2021-09-03 | Sreekuttan O M | Coding | 3- Completed | 2.5 | 1 | 1.5
| T2 | Search Products based on product name | 2021-09-02 | 2021-09-03 | Sreekuttan O M | Coding | 3- Completed | 2 | 1 | 1
T3
T4
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work

## Sprint II Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 43 | 30 | 13 | 0
SPRINT 2 BACKLOG
US-12 | T1 | Project Configuration | 2021-09-07 | 2021-09-07 | Nikhila Juttu | Build | 3- Completed | 5 | 5
| T2 | Minor Enhancement | 2021-09-08 | 2021-09-09 | Nikhila Juttu | Build | 3- Completed | 1 | 0.5 | 0.5
| T3 | Deployment | 2021-09-08 | 2021-09-09 | Nikhila Juttu | General | 3- Completed | 7 | 4 | 3
US-13 | T1 | Project Configuration | 2021-09-07 | 2021-09-07 | Sreekuttan O M | Build | 3- Completed | 5 | 5
| T2 | Minor Enhancement | 2021-09-08 | 2021-09-09 | Sreekuttan O M | Build | 3- Completed | 1.5 | 0.5 | 1
| T3 | Deployment | 2021-09-08 | 2021-09-09 | Sreekuttan O M | General | 3- Completed | 8 | 4 | 4
US-14 | T1
|  | Project Configuration | 2021-09-07 | 2021-09-07 | Mayank Kumar Athia | Build | 3- Completed | 5.5 | 5.5
T2
|  | Minor Enhancement | 2021-09-08 | 2021-09-09 | Mayank Kumar Athia | Build | 3- Completed | 1 | 0.5 | 0.5
| T3 | Deployment | 2021-09-08 | 2021-09-09 | Mayank Kumar Athia | General | 3- Completed | 9 | 5 | 4
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work

## Retrospection
Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
2021-08-31 | 2021-09-13 | Nikhila Juttu | start commenting the controller | avoid unnecessary usagage of symbols in comment | good implementation of service and controller | started commenting
2021-08-31 | 2021-09-13 | Nikhila Juttu | start commenting in controller | commenting the logic in the program while presenting | good implementation of service and controller | start commenting
2021-08-31 | 2021-09-13 | Sreekuttan O M | implement exception to methods | giving unwanted endpoint message | commenting | started doing exception
2021-08-31 | 2021-09-13 | Sreekuttan O M | do exception in service | give meaningful message in endpoints | commenting | start working endpoint message and exceptions
2021-08-31 | 2021-09-13 | Mayank Kumar Athia | align the code properly | reduce spacing in between codes | code implementation | align code properly
2021-08-31 | 2021-09-13 | Mayank Kumar Athia | give proper format to code | reduce line spacing | usage of keywords for methods | coding format changed

## Product Backlog Grooming
Sprint | US ID | Points Discussed
1 | US 01 | data needed for registeration,how to implement validation,how to do the implementation of service and controller class,endpoint meassages, how to implement exceptions,dto class.
1 | US 02 | Data required for registration, how to implement validation, endpoint implementation,service class,dto class,regx epressions,exceptions
1 | US 03 | Implementation of login service class, dto and controller, exceptions, validation of data, user inputs.
1 | US 04 | implementation of service and controller,dto , exceptions endpoints, data needed,how to do integration between microservice, method required, outputs, final data reterival,sql details.
1 | US 05 | Methods needed to implement the details service and controller, integration of micro service with other micro service, validating data, endpoint , data required for the implementation sql script,final output,exception handling
1 | US 06 | methods to implement the functions, endpoint, Implementation controller and service class,integration between microservices,sql script,exception handling
1 | US 07 | Method to implement the login, data required, validation of the data, endpoint fetching,methods needed for doing login, exception handling
1 | US 08 | method needed for implementation,service controller classes, validation of data,endpoint,data required, sql scripts, how endpoints needed , integeration between other microservice,output messages.exception handling
1 | US 09 | method implementation, data required for the removal, endpoint message,exception handling
1 | US 10 | method implementation service and controller,validation of data, integration of microservice, exception handling ,data needed for the implementation,output message
1 | US 11 | method implementation service and controller , data needed for this implementation,endpoints final output, exception handdling
2 | US 12 | install and setting up of maven in the local machine, build and generating report using sonar,giithub , changing in application properties docker and build spec,deployment in aws , ecr ecs rdsand codepipeline, api gateway endpoints implementation,sql connection with rds

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
1 | US 01 | day 1 | Nikhila Juttu | discussion on given data, and sql script creation
1 | US 08 | day1 | Sreekuttan O M | discussion on the use cases and sql script creation
1 | US 05 | day 1 | Mayank Kumar Athia | discussion on given data, and sql script creation
1 | US 01 | day2 | Nikhila Juttu | discussion on class ms implementation and buyer registeration | data validation | bean validation api
1 | US 08 | day 2 | Sreekuttan O M | discussion on ms implemetation and methods | integration | resttemplate
1 | US 05 | day2 | Mayank Kumar Athia | discussion on class implementation and methods | integration | resttemplate
1 | US 02 03 04 | day 3 | Nikhila Juttu | discussed on seller registration buyer login and buyer action
1 | US 08 | day 3 | Sreekuttan O M | Discussed on product method implementation and integration with user
1 | US 05 | day 3 | Mayank Kumar Athia | discussed on order ms and integration other user ms
1 | US 06 07 | day 4 | Nikhila Juttu | discussed on the method implementation and testing | testing | junit and mockito
1 | US 08 | day 4 | Sreekuttan O M | discussed on the method implemetation and testing | testing | junit and mockito
1 | US 05 | day 4 | Mayank Kumar Athia | discussed on method and testing | testing | junit and mockito
1 | US 08 09 | day 5 | Nikhila Juttu | discussed on method implementation and integration
1 | US 11 | day 5 | Sreekuttan O M | discussed on method implementation and integration
1 | US 05 04 | day 5 | Mayank Kumar Athia | discussed on method implementation and integration
2 | US 11 | day 6 | Nikhila Juttu | discussed on sonar and maven build
2 | US 12 | day 6 | Sreekuttan O M | discussed on sonar and maven build
2 | US 13 | day 6 | Mayank Kumar Athia | discussed on sonar and maven build
2 | US 11 | day 7 | Nikhila Juttu | configure ms and build spec docker and deployement of microservice
2 | US 12 | day 7 | Sreekuttan O M | configure ms and build spec docker and deployement of microservice
2 | US 13 | day 7 | Mayank Kumar Athia | configure ms and build spec docker and deployement of microservice
2 | US 11 | day 8 | Nikhila Juttu | deployemnet on ms and gernerate endpoints in api gateway
2 | US 12 | day 8 | Sreekuttan O M | deployemnet on ms and gernerate endpoints in api gateway
2 | US 13 | day 8 | Mayank Kumar Athia | deployemnet on ms and gernerate endpoints in api gateway